Table 6: SADCWaterLab work programme 2008

| Put presentations on the web and inform participants | Dec 07 | Michael |
| --- | --- | --- |
| MoU to be finalised | Jan 08 | Donald |
| recirculate questionnaire on used instrumentation | Feb 08 | Donald |
| search for useful used instrumentation | ongoing | Michael/Stefan |
| clarify local coordinators | Jan 08 | Donald |
| write new letter for nomination of local coordinators directly to institutions | Jan 08 | Donald |
| redesign PT leaflet | Feb 08 | Donald |
| microbiology PT according to work plan in report | announcement Jan 08 | Patricia |
| install mailing list | Jan 08 | Donald |
| PT provider to contact well performing labs in nitrate and phosphate to precisely describe their methods in the mailing list | Feb 08 | Merylinda |
| next chemistry PT | according to decided schedule announcement Feb 08 | Merylinda |
| evaluation workshop in Kampala (if not possible: Windhoek) | Nov/Dec 08 | all |
| promote the PT scheme | ongoing | all |
| raise awareness through national workshops | ongoing | all |